## Tasks
TASK | Participants | Hours | Joar | Márton | Alejandro | Cho | Rifat | Jonas | Gergely | Rasmus
Create the overleaf template | Jonas Rommel Attrup, Rasmus Beyer Andersen | 1 | [5 empty] | 1 | 0 | 1
After storing the IPs we pick 5 each to look into deeper using Shodan and other public tools | Jonas Rommel Attrup, Rasmus Beyer Andersen, Márton Reiter, Gergely Salomvári, Joar Belsnes, Alejandro Lozano Rebollo, Choeun Song | 75 | 10 | 10 | 10 | 15 |  | 10 | 20 | 10
Read repports given by S and take detailed notes | Jonas Rommel Attrup, Rasmus Beyer Andersen, Márton Reiter, Gergely Salomvári, Joar Belsnes, Alejandro Lozano Rebollo, Choeun Song | 23 | 2 | 2 | 6 | 5 |  | 5 | 3 | 4
Explore Firehol and look at its functionality | Jonas Rommel Attrup, Rasmus Beyer Andersen, Márton Reiter, Gergely Salomvári, Joar Belsnes, Alejandro Lozano Rebollo, Choeun Song | 8 | 1 | 1 | 1 | 2 |  | 2 | 1 | 1
Fixing overleaf template | Jonas Rommel Attrup, Rasmus Beyer Andersen | 1 | [5 empty] | 1 | 0 | 1
Make a Database in Postgres | Márton Reiter, Joar Belsnes, Jonas Rommel Attrup, Gergely Salomvári | 43 | 16 | 16 |  |  |  | 10 | 1 | 0
Fetch and put the IPs in our new Database | Jonas Rommel Attrup, Rasmus Beyer Andersen, Márton Reiter, Gergely Salomvári, Joar Belsnes, Alejandro Lozano Rebollo, Choeun Song | 5 | ?? | Isn't it the automated thing we do everyday? So basically no time from us, but the scripts are working instead |  |  |  | 5 | 0 | 0
Background research: Explain and research basic knowledge about IPs. How do they work basic basic. Use AAU bib for sources | Jonas Rommel Attrup, Rasmus Beyer Andersen | 10 | [5 empty] | 10 | 0 | 6
Read pdfs about subnetting Gery uploaded to discord | Joar Belsnes | 4 | 1 | 1 | 1 | 1 |  |  | 0 | 1
Read a little about the basics of SQL | Jonas Rommel Attrup, Rasmus Beyer Andersen, Márton Reiter, Gergely Salomvári, Joar Belsnes, Alejandro Lozano Rebollo, Choeun Song | 9 | 1 | 1 | 2 | 2 |  | 2 | 1 | 2
Create a Script for Step 3) which checks several IPs in different domains (VirusTotal, Shodan.io, MXToolBox, WhoIs, IPQualityScore.com etc) | Alejandro Lozano Rebollo, Rasmus Beyer Andersen, Gergely Salomvári, Márton Reiter | 17 |  |  | 10 |  |  |  | 7 | 8
Github Training camp | Gergely Salomvári, Márton Reiter, Choeun Song, Joar Belsnes | 7 | 2 | 2 |  | 2 |  |  | 1
Write Methodology part in report | Gergely Salomvári, Márton Reiter, Rasmus Beyer Andersen, Joar Belsnes | 15 | 2 | 2 |  |  |  |  | 11 | 4
Do background research on IP Blocklists (general) pros and cons | Choeun Song, Jonas Rommel Attrup | 20 |  |  |  | 10 |  | 10 | 0
Make a script to filter Danish blocked IPs and networks from the aggregated firehol blocklist. | Gergely Salomvári, Jonas Rommel Attrup | 25 | [5 empty] | 10 | 15
Make the OSINTscript to accept txt files | Gergely Salomvári, Márton Reiter, Jonas Rommel Attrup, Rasmus Beyer Andersen | 16 |  | 1 |  |  |  | 10 | 5 | 25
Configure SSH on Shreyas' laptop | Gergely Salomvári | 1 | [6 empty] | 1
Create scrpt to fetch blocked Ips | Márton Reiter | 5 |  | 5 |  |  |  |  | 0
Make a Script that transfers the txt file of blocked DK IPs, and the OSINT scripts txt files and add them to the database | Gergely Salomvári, Márton Reiter, Joar Belsnes, Alejandro Lozano Rebollo | 82 | 25 | 25 | 25 |  |  |  | 7 | 5
Fetching the data from abuseIPDB into the OSINT scripts. | Gergely Salomvári, Jonas Rommel Attrup | 36 | [5 empty] | 30 | 6 | 6
Write a script to check filtered IPs/networks origin with RIPE DB. | Gergely Salomvári | 18 | [6 empty] | 18 | 4
Write a document about the methodology and the scripts and their connections. (Google Drive) | Gergely Salomvári | 8 | [6 empty] | 8
Restructure DB | Márton Reiter, Joar Belsnes, Rasmus Beyer Andersen | 12 | 6 | 6 |  |  |  |  | 0 | 4
Make the plottings | Gergely Salomvári, Jonas Rommel Attrup, Joar Belsnes | 97 | 28 | 28 |  |  |  | 30 | 11
Make your own opinion of the results we have come to in excel and the graphs. | Jonas Rommel Attrup, Rasmus Beyer Andersen, Márton Reiter, Gergely Salomvári, Joar Belsnes, Alejandro Lozano Rebollo, Choeun Song, Showmik Islam Rifat | 37 | 2 | 2 | 6 | 5 | 9 | 10 | 3 | 4
Write Results part in report | Jonas Rommel Attrup, Joar Belsnes | 86 | 28 | 28 |  |  |  | 30 | 0
Write Discussion part in report | Joar Belsnes, Choeun Song | 62 | 16 | 16 |  | 30 |  |  | 0
Write Abstract part in report | Showmik Islam Rifat, Rasmus Beyer Andersen | 15 |  |  |  |  | 15 |  | 0 | 2
Write Introduction part in report | Showmik Islam Rifat, Rasmus Beyer Andersen | 12 |  |  |  |  | 12 |  | 0 | 3
Write Background Research part in report | Choeun Song, Márton Reiter, Alejandro Lozano Rebollo | 35 |  |  | 19 | 16 |  |  | 0 | 4
Write Related Work part in report | Alejandro Lozano Rebollo, Rasmus Beyer Andersen | 28 |  |  | 28 |  |  |  | 0 | 15
Write Conclusion part in report | Gergely Salomvári, Jonas Rommel Attrup | 9 | [5 empty] | 5 | 4
Write Acnowledgement part in report | Alejandro Lozano Rebollo | 3 |  |  | 3 |  |  |  | 0
Write script to get ASN names for the IPs | Gergely Salomvári | 12 | [6 empty] | 12
Look into the N/A category of Usage type from IPABUSE (take small handfull of those and look why they are in the blocklist) | Showmik Islam Rifat, Choeun Song | 35 |  |  |  | 10 | 25 |  | 0
Look at the top 5 most reported IPs (Could be TOR), investigate them further. | Gergely Salomvári, Jonas Rommel Attrup, Joar Belsnes | 26 | [5 empty] | 10 | 16
The 5 most reported IPs that are not TOR | Jonas Rommel Attrup, Joar Belsnes | 18 | 4 | 4 |  |  |  | 10 | 0
Look at the 26 IP's that got off the blocklist after one day | Alejandro Lozano Rebollo, Rasmus Beyer Andersen | 9 |  |  | 9 |  |  |  | 0 | 9
Look into the ones that got on, off and on again | Alejandro Lozano Rebollo, Rasmus Beyer Andersen | 13 |  |  | 13 |  |  |  | 0 | 10
The sudden drop off on november 23 | Márton Reiter | 5 |  | 5 |  |  |  |  | 0
The most network prefix on blocklist | Gergely Salomvári | 8 | [6 empty] | 8
Work on Shreiya's and Edlira feedback from the report, taking care of our assigned sections | Jonas Rommel Attrup, Rasmus Beyer Andersen, Márton Reiter, Gergely Salomvári, Joar Belsnes, Alejandro Lozano Rebollo, Choeun Song, Showmik Islam Rifat | 70 | 6 | 6 | 13 | 11 | 11 | 10 | 13 | 10
Database restructure | Joar Belsnes,Gergely Salomvári | 20 | 8 | 8 |  |  |  |  | 4
Research paper structure | Jonas Rommel Attrup, Rasmus Beyer Andersen | 1 | [5 empty] | 1 | 0 | 1
Design the plots | Gergely Salomvári, Jonas Rommel Attrup, Joar Belsnes | 26 | 4 | 4 |  |  |  | 10 | 8
Figure out cron job | Jonas Rommel Attrup | 2 |  |  |  | 1 |  | 1 | 0
Testing the script individually | Gergely Salomvári, Márton Reiter | 9 |  | 3 |  |  |  |  | 6
Testing the setup on the remote PC | Gergely Salomvári, Jonas Rommel Attrup, Joar Belsnes | 44 | 6 | 6 |  |  |  | 20 | 12
Writing the bash script | Joar Belsnes | 2 | 1 | 1 |  |  |  |  | 0
Comment each others sections constructively | Jonas Rommel Attrup, Rasmus Beyer Andersen, Márton Reiter, Gergely Salomvári, Joar Belsnes, Alejandro Lozano Rebollo, Choeun Song, Showmik Islam Rifat | 39 | 4 | 4 | 5 | 5 | 8 | 5 | 8 | 4
Help others: to understand networking basics and with their asks | Gergely Salomvári | [7 empty] | 20
Investigate delisting methods for blocklists | Gergely Salomvári | [7 empty] | 8
WORKING HOUR PER MEMBER |  | 1164 | 173 | 187 | 151 | 115 | 80 | 248 | 238 | 144